## Actions
# | Item | Owner | Due | Status
1 | Turbine installation readiness 2027 – input | Fraser Mackenzie | 2026-08-25 | Blocked
2 | Millbrook planning conditions – review | Isla Watson | 2026-09-04 | Blocked
3 | Export cable 2 recovery plan (HB-RISK-017) – check | Scott Walker | 2026-08-08 | In progress
4 | Change order CO-007 assessment – input | Sebastian Brockmann | 2026-07-23 | Blocked
5 | Port of Eastholm laydown plan – approval | Fraser Mackenzie | 2026-08-13 | Done
6 | Port of Eastholm laydown plan – check | Kwame Mensah | 2026-08-25 | Blocked