## Actions
# | Item | Owner | Due | Status
1 | Monopile fabrication status – approval | Paula Lange | 2026-03-23 | Blocked
2 | Transition piece delivery plan – review | Jonas Neumann | 2026-03-17 | Done
3 | Monopile fabrication status – update | Laura Lehmann | 2026-03-13 | Done
4 | Weld inspection summary – update | Anna Becker | 2026-02-21 | Done
5 | Monopile fabrication status – approval | Antje Peters | 2026-02-09 | Blocked
6 | Monopile fabrication status – check | Stefan Möller | 2026-03-05 | Done
7 | Monopile fabrication status – update | Julia Hansen | 2026-03-01 | Open
8 | Weld inspection summary – check | Paula Lange | 2026-02-23 | Done
9 | Weld inspection summary – input | Hendrik Petersen | 2026-02-23 | Blocked
10 | Transition piece delivery plan – approval | Kai Ehlers | 2026-03-26 | Done
11 | Transition piece delivery plan – check | Agnieszka Kamiński | 2026-03-11 | Done