## Actions
# | Item | Owner | Due | Status
1 | Audit planning memo – approval | Jonas Schulz | 2026-06-09 | Done
2 | PBC list – check | Maren Behrens | 2026-04-27 | In progress
3 | Audit planning memo – approval | Christian Schneider | 2026-05-03 | Blocked
4 | Audit planning memo – approval | Andreas Lehmann | 2026-04-29 | Done
5 | PBC list – review | Greta Thomsen | 2026-04-26 | In progress
6 | PBC list – review | Kai Möller | 2026-05-22 | In progress
7 | Interim audit findings – review | Kai Möller | 2026-05-25 | In progress
8 | PBC list – review | Kai Möller | 2026-05-23 | Open
9 | Audit planning memo – approval | Jonas Schulz | 2026-04-30 | Blocked
10 | PBC list – input | Andreas Lehmann | 2026-05-04 | Done