## Actions
# | Item | Owner | Due | Status
1 | Consultation response summary – check | Sophie Gray | 2026-09-12 | Done
2 | Planning condition queries – check | Paul Johnston | 2026-09-19 | In progress
3 | Consultation response summary – review | Kieran Watson | 2026-11-10 | Done
4 | Consultation response summary – input | Kieran Watson | 2026-11-01 | Done
5 | Planning condition queries – check | Paul Johnston | 2026-10-22 | Open
6 | Consultation response summary – input | Andrew Campbell | 2026-09-23 | Done