## Actions
# | Item | Owner | Due | Status
1 | Marine mammal observer log – approval | Dr. Rachel Moss | 2026-01-17 | Open
2 | Marine mammal observer log – review | Scott Duncan | 2026-01-19 | In progress
3 | Seabird survey notes – check | Kirsty Murray | 2025-12-28 | Blocked
4 | Marine mammal observer log – input | Claire Smith | 2025-12-25 | Open
5 | Seabird survey notes – update | Catriona Ross | 2026-01-16 | Blocked
6 | Skylark survey data – approval | Connor Hughes | 2025-12-06 | Done
7 | Marine mammal observer log – update | Craig Ferguson | 2025-12-14 | Open
8 | Skylark survey data – approval | Holly Mackenzie | 2026-01-24 | Blocked