## Actions
# | Item | Owner | Due | Status
1 | Floating wind technology watch – input | Anne Sørensen | 2026-10-31 | Done
2 | Floating wind technology watch – check | Thomas Christensen | 2026-10-04 | In progress
3 | Met mast data QA – approval | Zara Chen | 2026-11-07 | In progress
4 | Wake loss sensitivity – check | Niklas Köhler | 2026-09-14 | Open
5 | Met mast data QA – approval | Maja Andersson | 2026-10-17 | Done
6 | Wake loss sensitivity – input | Marianne Hansen | 2026-10-24 | Done
7 | SCADA tag list – update | Elena Sato | 2026-09-19 | Blocked
8 | Wake loss sensitivity – check | Jonas Christensen | 2026-10-01 | Blocked
9 | Monopile fatigue check – input | Thomas Mortensen | 2026-09-24 | Done
10 | Met mast data QA – check | Hendrik Schmidt | 2026-10-12 | In progress
11 | Wake loss sensitivity – input | Sofie Lindqvist | 2026-10-13 | In progress