## Actions
# | Item | Owner | Due | Status
1 | Ice detection settings – approval | Olga Kowalczyk | 2026-04-28 | Done
2 | Kestrel Ridge availability – update | Ole Hartmann | 2026-05-27 | Done
3 | Kestrel Ridge availability – approval | Liam Smith | 2026-06-08 | Done
4 | Control room handover – approval | Astrid Mortensen | 2026-05-14 | Done
5 | Ice detection settings – check | Frederik Petersen | 2026-05-15 | Done
6 | T-07 gearbox lessons learned – check | Paweł Kamiński | 2026-04-18 | Done
7 | Spare parts min/max levels – update | Scott Jones | 2026-06-04 | In progress
8 | T-07 gearbox lessons learned – update | Morag Wood | 2026-04-24 | Done
9 | Ice detection settings – review | Scott Jones | 2026-04-28 | In progress