## Actions
# | Item | Owner | Due | Status
1 | Skylark survey data – approval | Claire Smith | 2026-11-06 | Open
2 | Skylark survey data – review | Scott Duncan | 2026-10-10 | Done
3 | Seabird survey notes – review | Lucy Brown | 2026-11-03 | Done
4 | Skylark survey data – review | Lucy Brown | 2026-11-03 | In progress
5 | Seabird survey notes – check | Connor Hughes | 2026-10-06 | Open
6 | Seabird survey notes – check | Calum Hughes | 2026-09-16 | Done