## Actions
# | Item | Owner | Due | Status
1 | Harrow Bay monopile campaign – check | Elena Dubois | 2026-01-07 | Blocked
2 | Millbrook planning conditions – check | Camilla Thomsen | 2025-12-19 | Done
3 | Export cable 2 recovery plan (HB-RISK-017) – review | Robert Macdonald | 2026-01-13 | Done
4 | Interface matrix Halden / Norfab – approval | Magnus Nielsen | 2026-01-20 | Done
5 | Millbrook planning conditions – update | Magdalena Zieliński | 2026-01-10 | Done
6 | Change order CO-007 assessment – review | Ross Smith | 2025-12-11 | Blocked
7 | Turbine installation readiness 2027 – input | Ingrid Solberg | 2026-01-22 | Done
8 | Weekly progress report inputs – input | Kieran Duncan | 2025-11-27 | Blocked
9 | Export cable 2 recovery plan (HB-RISK-017) – approval | Amelia Hughes | 2026-01-07 | Blocked
10 | Weekly progress report inputs – review | Duncan Wood | 2025-12-02 | In progress
11 | Weekly progress report inputs – update | Greta Fischer | 2025-11-28 | Done
12 | Millbrook planning conditions – input | David Roberts | 2026-01-19 | Blocked