## Actions
# | Item | Owner | Due | Status
1 | Tracker supplier comparison – update | Fiona Grant | 2026-05-17 | In progress
2 | EPC programme draft – approval | Euan Henderson | 2026-04-30 | Blocked
3 | EPC programme draft – review | Heather Wood | 2026-05-28 | Done
4 | Tracker supplier comparison – check | Stuart Young | 2026-04-29 | Blocked
5 | Tracker supplier comparison – update | Sofia Chen | 2026-05-12 | Done
6 | Millbrook layout revision – check | Arjun Sato | 2026-05-17 | In progress
7 | Millbrook layout revision – check | Ailsa Graham | 2026-06-02 | Done
8 | Tracker supplier comparison – approval | Stuart Reid | 2026-04-23 | In progress
9 | EPC programme draft – approval | Freya Clark | 2026-04-23 | Done
10 | EPC programme draft – check | David Davies | 2026-06-14 | Done
11 | EPC programme draft – update | Sofia Chen | 2026-05-30 | Done