Harrow Bay – talking points for the board

For Amara, board meeting October 2026 – draft

Elena Márquez  ·  03 October 2026

# Headline

Harrow Bay is two piles behind the foundation baseline after a very stormy September, but the recovery plan is approved and first power on 30 September 2027 is not at risk. Budget remains EUR 1,620 m.

# Three points

Progress: 14 of 40 monopiles installed (HB-A14 on 30 Sep), offshore substation topside installed 19 Aug. Recovery: Sea Atlas option 2 and 24/7 piling once the fatigue plan is approved.

HB-RISK-017 (export cable 2): re-manufacture on track for 12 March 2027. Commercial: Severn accepts ~EUR 4.1 m of CO-010; LD start date still disputed. CEO-level meeting may be needed – Amara, are you OK to join?

Money: EUR 790 m spent; EAC EUR 1,620 m; contingency EUR 31.4 m left. LD recovery (~EUR 4.2 m) is upside, not in the numbers.

# If asked

Safety: 0 LTIs; the June near miss is closed, all 8 actions done

Environment: noise compliant except one pile in April; porpoise data reassuring

PPA with Arcturus Steel: no impact – PPA starts at COD 2028