## Actions
# | Item | Owner | Due | Status
1 | Energy yield review comments – check | Fiona Watson | 2025-11-25 | In progress
2 | Construction risk notes – check | Sara Andersson | 2025-12-04 | Open
3 | LTA monthly review – update | Craig Evans | 2025-10-18 | In progress
4 | Energy yield review comments – review | Hamish Taylor | 2025-11-10 | In progress
5 | Construction risk notes – review | Gustav Eriksson | 2025-11-29 | In progress
6 | LTA monthly review – input | Fiona Watson | 2025-12-16 | Done
7 | Energy yield review comments – approval | Nicola Clark | 2025-11-21 | Blocked
8 | Construction risk notes – input | Fiona Watson | 2025-12-10 | In progress
9 | Construction risk notes – update | Craig Evans | 2025-11-01 | In progress