## Actions
# | Item | Owner | Due | Status
1 | Weld inspection summary – review | Florian Jensen | 2026-11-02 | Done
2 | Weld inspection summary – input | Joanna Nowak | 2026-11-08 | Done
3 | Monopile fabrication status – approval | Hendrik Petersen | 2026-10-26 | Done
4 | Weld inspection summary – review | Paula Lange | 2026-10-03 | Open
5 | Transition piece delivery plan – update | Agnieszka Wójcik | 2026-11-07 | Blocked