## Actions
# | Item | Owner | Due | Status
1 | Turbine installation readiness 2027 – input | Kate Davies | 2026-09-07 | Done
2 | Turbine installation readiness 2027 – update | Craig Campbell | 2026-09-18 | Open
3 | Port of Eastholm laydown plan – approval | Felix Brandt | 2026-10-27 | Blocked
4 | Interface matrix Halden / Norfab – approval | Eilidh Graham | 2026-09-16 | Open
5 | Turbine installation readiness 2027 – update | Jonas Dahl | 2026-10-17 | Done