## Actions
# | Item | Owner | Due | Status
1 | Jacket inspection – review | Tone Hansen | 2026-02-05 | Done
2 | Topside commissioning status – approval | Hilde Solberg | 2026-03-23 | Done
3 | Jacket inspection – check | Erik Moen | 2026-03-25 | Open
4 | HB-OSS punch list – input | Håkon Lie | 2026-03-25 | Blocked
5 | Jacket inspection – update | Marte Moen | 2026-03-08 | Done
6 | Jacket inspection – check | Kari Bakke | 2026-02-22 | Done
7 | Topside commissioning status – input | Håkon Moen | 2026-03-29 | In progress