## Actions
# | Item | Owner | Due | Status
1 | Transition piece delivery plan – input | Michael Peters | 2026-10-18 | Blocked
2 | Transition piece delivery plan – update | Jonas Neumann | 2026-10-16 | Done
3 | Weld inspection summary – review | Jonas Neumann | 2026-10-17 | Blocked
4 | Weld inspection summary – approval | Jana Hansen | 2026-10-26 | Open
5 | Monopile fabrication status – review | Tim Klein | 2026-10-01 | Done
6 | Weld inspection summary – check | Agnieszka Kamiński | 2026-10-26 | Open
7 | Monopile fabrication status – input | Fabian Peters | 2026-09-05 | Done
8 | Monopile fabrication status – check | Malte Friedrich | 2026-10-05 | Done
9 | Transition piece delivery plan – review | Tim Klein | 2026-10-25 | Open