## Actions
# | Item | Owner | Due | Status
1 | Met mast data QA – update | Karin Berglund | 2026-11-07 | Done
2 | Geotechnical boulder field – update | Zara Rossi | 2026-09-13 | Done
3 | SCADA tag list – approval | Gustav Andersson | 2026-10-29 | Blocked
4 | Met mast data QA – approval | Gustav Andersson | 2026-11-11 | Blocked
5 | Geotechnical boulder field – check | Andreas Schmidt | 2026-09-14 | Done
6 | Monopile fatigue check – approval | Priya Nguyen | 2026-10-23 | Done
7 | Design basis review comments – approval | Jack Wright | 2026-10-13 | In progress
8 | SCADA tag list – review | Emre Singh | 2026-11-03 | Blocked
9 | SCADA tag list – update | Tomasz Zieliński | 2026-10-11 | Done
10 | SCADA tag list – review | Thomas Christensen | 2026-10-31 | Blocked
11 | Monopile fatigue check – check | Signe Jørgensen | 2026-10-09 | In progress
12 | SCADA tag list – check | Thomas Mortensen | 2026-09-21 | Done
13 | Design basis review comments – check | Robert Walker | 2026-11-01 | In progress