## Actions
# | Item | Owner | Due | Status
1 | Turbine installation readiness 2027 – update | Kirsty Hall | 2025-11-17 | Done
2 | Export cable 2 recovery plan (HB-RISK-017) – approval | Anja Neumann | 2025-11-17 | Done
3 | Change order CO-007 assessment – input | Craig Brown | 2025-11-11 | Done
4 | Turbine installation readiness 2027 – input | Amara Popescu | 2025-11-25 | Open
5 | Port of Eastholm laydown plan – update | Gordon Jones | 2025-12-05 | Blocked
6 | Millbrook planning conditions – approval | Anna Jensen | 2025-11-20 | Done
7 | Interface matrix Halden / Norfab – input | Sebastian Brockmann | 2025-11-22 | Open
8 | Millbrook planning conditions – input | Greta Fischer | 2025-11-25 | Blocked
9 | Port of Eastholm laydown plan – input | Magdalena Zieliński | 2025-11-26 | Done
10 | Interface matrix Halden / Norfab – check | Nikolai Moreau | 2025-10-21 | In progress
11 | Harrow Bay monopile campaign – approval | Camilla Thomsen | 2025-10-25 | Open