## Actions
# | Item | Owner | Due | Status
1 | Port of Eastholm laydown plan – input | Liam McAllister | 2026-04-14 | Open
2 | Port of Eastholm laydown plan – approval | Mikkel Jensen | 2026-05-24 | Done
3 | Change order CO-007 assessment – approval | Lewis Ross | 2026-04-23 | In progress
4 | Port of Eastholm laydown plan – review | Graham Watson | 2026-06-03 | Done
5 | Millbrook planning conditions – approval | Lewis Ross | 2026-04-10 | Done
6 | Turbine installation readiness 2027 – approval | Siobhan Watson | 2026-05-26 | Done