## Actions
# | Item | Owner | Due | Status
1 | Millbrook planning conditions – review | Graham Watson | 2026-02-21 | Open
2 | Change order CO-007 assessment – review | David Roberts | 2026-03-25 | Blocked
3 | Weekly progress report inputs – check | Emma Mitchell | 2026-04-07 | Blocked
4 | Weekly progress report inputs – approval | Jamie Morrison | 2026-04-12 | Open
5 | Harrow Bay monopile campaign – review | Anja Neumann | 2026-03-16 | Done
6 | Change order CO-007 assessment – update | Michael Friedrich | 2026-04-01 | In progress
7 | Millbrook planning conditions – approval | Nikolai Moreau | 2026-03-01 | In progress
8 | Harrow Bay monopile campaign – approval | Felix Brandt | 2026-03-27 | Done