## Actions
# | Item | Owner | Due | Status
1 | Factory acceptance test report – check | Robert Hughes | 2026-09-15 | In progress
2 | Export cable 2 re-manufacture plan – update | Ross Davies | 2026-11-05 | Done
3 | Cable lay sequence – review | Thomas Young | 2026-09-28 | Open
4 | Cable lay sequence – approval | Lewis Wilson | 2026-10-14 | Done
5 | Cable lay sequence – review | Ross Davies | 2026-10-16 | Blocked
6 | Cable lay sequence – check | Fraser McLean | 2026-10-13 | Open
7 | Cable lay sequence – input | Nicola Young | 2026-09-14 | Open
8 | Export cable 2 re-manufacture plan – input | Paul Graham | 2026-11-05 | Blocked
9 | Cable lay sequence – review | Stuart Fraser | 2026-09-13 | In progress
10 | Export cable 2 re-manufacture plan – review | James Brown | 2026-10-19 | Blocked
11 | Export cable 2 re-manufacture plan – review | Euan Watson | 2026-10-18 | Done