## Actions
# | Item | Owner | Due | Status
1 | Interface matrix Halden / Norfab – check | Lewis Ross | 2026-03-12 | Open
2 | Interface matrix Halden / Norfab – input | Rebecca Johnston | 2026-04-28 | Blocked
3 | Harrow Bay monopile campaign – approval | Sebastian Brockmann | 2026-04-12 | Done
4 | Weekly progress report inputs – approval | Duncan Roberts | 2026-04-19 | Blocked
5 | Export cable 2 recovery plan (HB-RISK-017) – update | Isabel Ferreira | 2026-03-14 | Blocked
6 | Export cable 2 recovery plan (HB-RISK-017) – update | Frank Krüger | 2026-04-09 | Done
7 | Turbine installation readiness 2027 – update | Joaquín Ivanova | 2026-05-07 | Done
8 | Interface matrix Halden / Norfab – check | Hannah Gray | 2026-04-06 | Done
9 | Harrow Bay monopile campaign – update | Calum Gray | 2026-04-08 | Open