## Actions
# | Item | Owner | Due | Status
1 | Wake loss sensitivity – input | Jesper Bach | 2026-10-24 | In progress
2 | Wake loss sensitivity – review | Henrik Andersen | 2026-10-19 | Done
3 | Geotechnical boulder field – update | Sofie Lindqvist | 2026-10-06 | In progress
4 | Array cable routing options – check | Signe Jørgensen | 2026-11-10 | Open
5 | Geotechnical boulder field – update | Niels Jørgensen | 2026-09-19 | In progress
6 | Met mast data QA – approval | Emma Pedersen | 2026-10-30 | Done
7 | Floating wind technology watch – approval | Oliver Grant | 2026-10-12 | Open
8 | Design basis review comments – check | David Thomson | 2026-10-16 | Done
9 | Floating wind technology watch – review | Anna Schmitt | 2026-11-06 | Open
10 | Array cable routing options – check | Siobhan Brown | 2026-10-11 | Done
11 | Wake loss sensitivity – check | Anne Sørensen | 2026-11-11 | Done
12 | Floating wind technology watch – approval | Siobhan Brown | 2026-10-06 | Done
13 | Floating wind technology watch – update | Jesper Bach | 2026-10-23 | Open