## Actions
# | Item | Owner | Due | Status
1 | Export cable 2 recovery plan (HB-RISK-017) – input | Craig Campbell | 2026-04-16 | Open
2 | Turbine installation readiness 2027 – check | Iain Davies | 2026-04-25 | Done
3 | Change order CO-007 assessment – update | Graham Watson | 2026-05-24 | Blocked
4 | Weekly progress report inputs – input | Ross Smith | 2026-04-22 | Done
5 | Harrow Bay monopile campaign – review | Liam Young | 2026-05-24 | Open
6 | Turbine installation readiness 2027 – update | Kirsty Hall | 2026-05-07 | Blocked
7 | Harrow Bay monopile campaign – approval | Ryan Baker | 2026-04-30 | Done
8 | Export cable 2 recovery plan (HB-RISK-017) – approval | Sophie Brandt | 2026-05-25 | Blocked
9 | Turbine installation readiness 2027 – approval | Duncan Wood | 2026-04-11 | Done
10 | Interface matrix Halden / Norfab – approval | Gemma Young | 2026-05-09 | Done