## Actions
# | Item | Owner | Due | Status
1 | Spare parts min/max levels – review | Patrick Doyle | 2026-08-07 | Blocked
2 | Control room handover – review | Leila Haddad | 2026-08-28 | In progress
3 | Blade inspection campaign – approval | Paul Burns | 2026-08-20 | In progress
4 | T-07 gearbox lessons learned – input | Oliver Hamilton | 2026-10-01 | Blocked
5 | Control room handover – review | Nadine Richter | 2026-08-28 | Open