## Actions
# | Item | Owner | Due | Status
1 | Interface matrix Halden / Norfab – update | Emma Mitchell | 2026-07-31 | Blocked
2 | Port of Eastholm laydown plan – input | Julia Köhler | 2026-08-02 | Blocked
3 | Turbine installation readiness 2027 – input | Grace Fraser | 2026-07-15 | Blocked
4 | Change order CO-007 assessment – update | Grace Brown | 2026-07-20 | In progress
5 | Change order CO-007 assessment – approval | Freya Kennedy | 2026-07-31 | Open
6 | Weekly progress report inputs – input | Jakob Johansen | 2026-07-25 | Open
7 | Port of Eastholm laydown plan – check | Freya Kennedy | 2026-08-08 | Done
8 | Port of Eastholm laydown plan – approval | Maren Lange | 2026-08-20 | Done