## Actions
# | Item | Owner | Due | Status
1 | PPE audit – check | Morag Anderson | 2026-08-17 | Blocked
2 | HSE-INC-2026-018 actions – input | Frederik Møller | 2026-08-11 | Open
3 | Bubble curtain monitoring – update | Theresa Kaiser | 2026-07-14 | Open
4 | PPE audit – review | Clara Neumann | 2026-06-25 | Done
5 | PPE audit – input | Heather Evans | 2026-06-24 | Done
6 | Bubble curtain monitoring – update | Euan Kerr | 2026-06-30 | In progress
7 | PPE audit – update | Emre Rahman | 2026-08-16 | Done
8 | Toolbox talk – dropped objects – approval | Olivia Wood | 2026-07-01 | Open