## Actions
# | Item | Owner | Due | Status
1 | Commissioning plan – input | Felix Meyer | 2025-11-08 | Blocked
2 | Installation manual comments – update | Søren Rasmussen | 2025-10-31 | In progress
3 | Commissioning plan – input | Søren Andersen | 2025-11-05 | Blocked
4 | Commissioning plan – approval | Sofie Dahl | 2025-11-25 | Done
5 | HTS-12 delivery schedule – review | Greta Jensen | 2025-11-11 | Done
6 | Commissioning plan – approval | Mikkel Dahl | 2025-12-13 | Open
7 | HTS-12 delivery schedule – update | Mikkel Larsen | 2025-12-22 | Done
8 | HTS-12 delivery schedule – update | Jonas Lund | 2025-10-29 | In progress
9 | Installation manual comments – input | Greta Becker | 2025-12-15 | Done
10 | Commissioning plan – approval | Lars Henriksen | 2025-11-27 | In progress
11 | Commissioning plan – input | Maja Petersen | 2025-11-24 | In progress
12 | Installation manual comments – review | Rasmus Sørensen | 2025-12-25 | Done