## Actions
# | Item | Owner | Due | Status
1 | Port of Eastholm laydown plan – check | Ingrid Solberg | 2026-10-19 | Open
2 | Export cable 2 recovery plan (HB-RISK-017) – approval | Vikram Costa | 2026-10-05 | Done
3 | Millbrook planning conditions – approval | Camilla Thomsen | 2026-09-26 | In progress
4 | Turbine installation readiness 2027 – check | Isla Watson | 2026-09-12 | In progress
5 | Weekly progress report inputs – input | Mikkel Jensen | 2026-09-26 | In progress
6 | Harrow Bay monopile campaign – update | Birgit Schwarz | 2026-09-14 | Open
7 | Turbine installation readiness 2027 – review | Grace Fraser | 2026-10-16 | Blocked
8 | Millbrook planning conditions – update | Kwame Mensah | 2026-10-30 | Done
9 | Export cable 2 recovery plan (HB-RISK-017) – update | Anna Jensen | 2026-10-04 | In progress
10 | Weekly progress report inputs – approval | Gemma Kerr | 2026-09-12 | Blocked