## Actions
# | Item | Owner | Due | Status
1 | Contract register clean-up – review | Clara Möller | 2026-09-11 | Open
2 | NDA review queue – approval | Magnus Poulsen | 2026-09-07 | In progress
3 | PPA WE-PPA-2026-004 obligations – approval | Priya Nair | 2026-07-22 | Open
4 | Contract register clean-up – approval | Ryan Kerr | 2026-08-20 | Done
5 | PPA WE-PPA-2026-004 obligations – input | Antje Friedrich | 2026-09-07 | Open
6 | PPA WE-PPA-2026-004 obligations – update | Clara Möller | 2026-09-06 | Done
7 | PPA WE-PPA-2026-004 obligations – review | Priya Nair | 2026-08-22 | Done
8 | NDA review queue – review | Priya Nair | 2026-08-17 | Open
9 | Contract register clean-up – approval | Freya Watson | 2026-09-11 | Open