## Actions
# | Item | Owner | Due | Status
1 | Met mast data QA – review | Zara Rossi | 2026-09-22 | Open
2 | Design basis review comments – input | Hannah Wilson | 2026-08-20 | Done
3 | Met mast data QA – input | Jonas Pedersen | 2026-09-12 | Done
4 | Floating wind technology watch – update | Priya Nguyen | 2026-08-29 | Done
5 | Wake loss sensitivity – input | Chloe Watson | 2026-08-29 | Blocked
6 | Array cable routing options – approval | Karen Lund | 2026-08-31 | Done
7 | SCADA tag list – check | Louise Bach | 2026-09-07 | Open
8 | Wake loss sensitivity – input | Karin Berglund | 2026-09-11 | Blocked
9 | Array cable routing options – input | Luca Patel | 2026-08-01 | Done
10 | Design basis review comments – check | Rosie Morrison | 2026-08-27 | Done
11 | Wake loss sensitivity – update | Luca Patel | 2026-08-30 | In progress
12 | Wake loss sensitivity – approval | David Thomson | 2026-09-03 | Blocked