## Actions
# | Item | Owner | Due | Status
1 | Commissioning plan – check | Felix Meyer | 2025-10-26 | Done
2 | Commissioning plan – input | Martin Christensen | 2025-12-19 | Done
3 | Installation manual comments – update | Jakob Petersen | 2025-12-09 | Done
4 | Commissioning plan – update | Rasmus Sørensen | 2025-12-22 | In progress
5 | Commissioning plan – check | Maja Jensen | 2025-12-06 | Blocked
6 | Commissioning plan – input | Jannik Thomsen | 2025-11-01 | Done
7 | Commissioning plan – check | Emil Vestergaard | 2025-12-11 | Done
8 | HTS-12 delivery schedule – approval | Ida Olsen | 2025-11-10 | Blocked