## Actions
# | Item | Owner | Due | Status
1 | Export cable 2 recovery plan (HB-RISK-017) – review | Kwame Mensah | 2026-05-31 | Blocked
2 | Millbrook planning conditions – update | Camilla Dahl | 2026-04-26 | Done
3 | Turbine installation readiness 2027 – input | Eilidh Wright | 2026-04-30 | Open
4 | Weekly progress report inputs – check | Frank Krüger | 2026-06-04 | Open
5 | Interface matrix Halden / Norfab – input | Vikram Costa | 2026-05-14 | Open