## Actions
# | Item | Owner | Due | Status
1 | Installation manual comments – review | Mikkel Dahl | 2026-07-13 | Open
2 | Installation manual comments – check | Anders Lund | 2026-08-08 | Blocked
3 | Commissioning plan – input | Felix Meyer | 2026-08-10 | In progress
4 | HTS-12 delivery schedule – update | Martin Thomsen | 2026-07-20 | Done
5 | HTS-12 delivery schedule – approval | Ida Hansen | 2026-07-29 | Done
6 | Commissioning plan – approval | Kasper Holm | 2026-08-20 | Open
7 | HTS-12 delivery schedule – check | Mikkel Larsen | 2026-09-11 | Open
8 | Installation manual comments – review | Maja Kristensen | 2026-08-14 | Done
9 | Commissioning plan – update | Leila Novak | 2026-08-20 | In progress
10 | Commissioning plan – review | Ida Olsen | 2026-07-14 | Done
11 | Installation manual comments – review | Lars Henriksen | 2026-09-07 | Done