## Actions
# | Item | Owner | Due | Status
1 | Export cable 2 re-manufacture plan – input | Stuart Walker | 2026-11-09 | Done
2 | Cable lay sequence – approval | Sofia Novak | 2026-11-01 | In progress
3 | Export cable 2 re-manufacture plan – input | Lewis Wilson | 2026-10-20 | Done
4 | Export cable 2 re-manufacture plan – update | Kirsty Paterson | 2026-11-05 | Open
5 | Cable lay sequence – approval | Fraser McLean | 2026-11-09 | Blocked
6 | Factory acceptance test report – review | Stuart Walker | 2026-10-24 | Open
7 | Export cable 2 re-manufacture plan – review | Joaquín Novak | 2026-11-04 | Blocked
8 | Factory acceptance test report – review | Lewis Walker | 2026-10-12 | Blocked