## Actions
# | Item | Owner | Due | Status
1 | Millbrook planning conditions – input | Amara Popescu | 2026-07-12 | Blocked
2 | Millbrook planning conditions – approval | Camilla Dahl | 2026-07-15 | Open
3 | Weekly progress report inputs – approval | David Roberts | 2026-07-28 | In progress
4 | Weekly progress report inputs – update | Craig Campbell | 2026-07-09 | Done
5 | Millbrook planning conditions – approval | Jamie Morrison | 2026-08-11 | Open
6 | Millbrook planning conditions – review | Joaquín Ivanova | 2026-07-30 | Blocked
7 | Change order CO-007 assessment – review | Iain Taylor | 2026-07-29 | Blocked
8 | Change order CO-007 assessment – check | Mark Reid | 2026-07-29 | Done
9 | Change order CO-007 assessment – input | Svenja Richter | 2026-07-29 | In progress
10 | Export cable 2 recovery plan (HB-RISK-017) – update | Jonas Dahl | 2026-08-02 | In progress
11 | Interface matrix Halden / Norfab – check | Nikolai Moreau | 2026-08-06 | Done
12 | Change order CO-007 assessment – check | Jakob Johansen | 2026-08-21 | Done
13 | Millbrook planning conditions – review | Scott Walker | 2026-07-11 | Done