## Actions
# | Item | Owner | Due | Status
1 | Campaign visuals feedback – check | Tim Schneider | 2026-08-13 | Done
2 | Website wireframes – check | Daniel Petersen | 2026-08-14 | Done
3 | Annual report layout notes – approval | Antje Schmitt | 2026-08-14 | Blocked
4 | Campaign visuals feedback – input | Sören Behrens | 2026-08-08 | In progress
5 | Annual report layout notes – check | Martin Holm | 2026-09-23 | Done
6 | Campaign visuals feedback – review | Anna Lehmann | 2026-08-12 | Done
7 | Website wireframes – approval | Antje Schmitt | 2026-09-01 | Done
8 | Website wireframes – approval | Martin Holm | 2026-08-09 | Open
9 | Annual report layout notes – input | Sofie Kristensen | 2026-08-15 | Blocked
10 | Campaign visuals feedback – check | Daniel Becker | 2026-08-19 | Open
11 | Website wireframes – check | Tim Schneider | 2026-09-12 | Blocked
12 | Annual report layout notes – approval | Martin Holm | 2026-08-20 | Done