## Actions
# | Item | Owner | Due | Status
1 | Factory acceptance test report – update | Ross Burns | 2026-02-10 | Blocked
2 | Factory acceptance test report – input | Ross Robertson | 2025-12-15 | Done
3 | Factory acceptance test report – review | Siobhan Duncan | 2025-12-25 | Done
4 | Export cable 2 re-manufacture plan – input | Freya Scott | 2025-12-27 | Open
5 | Cable lay sequence – input | Lewis Walker | 2026-01-31 | Open
6 | Factory acceptance test report – review | Ravi Haddad | 2026-01-09 | Done
7 | Cable lay sequence – input | Euan Watson | 2026-02-12 | Blocked