## Actions
# | Item | Owner | Due | Status
1 | Toolbox talk – dropped objects – check | Morag Anderson | 2026-09-26 | Done
2 | HSE-INC-2026-018 actions – review | Emre Rahman | 2026-10-29 | Done
3 | Toolbox talk – dropped objects – update | Heather Evans | 2026-09-12 | In progress
4 | Site inspection findings – approval | Frederik Møller | 2026-10-27 | Open
5 | HSE-INC-2026-018 actions – check | Tim Dittmer | 2026-10-16 | In progress
6 | Site inspection findings – review | Theresa Kaiser | 2026-10-09 | Done
7 | Bubble curtain monitoring – review | Euan Kerr | 2026-09-13 | Done
8 | Toolbox talk – dropped objects – update | Hannah Weber | 2026-09-10 | Blocked
9 | Bubble curtain monitoring – approval | Clara Neumann | 2026-10-13 | Done
10 | HSE-INC-2026-018 actions – approval | Heather Evans | 2026-09-10 | Done
11 | Bubble curtain monitoring – update | Morten Pedersen | 2026-10-31 | Done
12 | Site inspection findings – approval | Heather Evans | 2026-09-20 | In progress