## Actions
# | Item | Owner | Due | Status
1 | Consultation response summary – approval | Catriona Thomson | 2026-08-08 | Open
2 | Planning condition queries – review | Hamish Ferguson | 2026-08-19 | Done
3 | Planning condition queries – review | Andrew Campbell | 2026-08-07 | Done
4 | Site visit notes – update | Kieran Watson | 2026-08-19 | Open
5 | Planning condition queries – update | Callum Robertson | 2026-08-14 | Blocked
6 | Planning condition queries – approval | Kieran Watson | 2026-08-28 | Done
7 | Site visit notes – approval | Lauren Duncan | 2026-09-03 | In progress