## Actions
# | Item | Owner | Due | Status
1 | Floating wind technology watch – input | Karen Lund | 2026-10-08 | In progress
2 | Design basis review comments – review | Isla Anderson | 2026-10-23 | Done
3 | Met mast data QA – approval | Theresa Brandt | 2026-09-28 | Done
4 | Floating wind technology watch – approval | Thomas Christensen | 2026-11-03 | Done
5 | Design basis review comments – approval | Louise Bach | 2026-10-02 | Done
6 | Design basis review comments – check | Jakob Andersen | 2026-10-22 | In progress
7 | Monopile fatigue check – update | Thomas Mortensen | 2026-11-05 | Done
8 | Geotechnical boulder field – review | Zara Chen | 2026-09-24 | Done
9 | SCADA tag list – update | Sofie Lindqvist | 2026-10-04 | Done