## Actions
# | Item | Owner | Due | Status
1 | Harrow Bay monopile campaign – check | Duncan Roberts | 2026-08-24 | Blocked
2 | Turbine installation readiness 2027 – review | Siobhan Watson | 2026-09-19 | Done
3 | Port of Eastholm laydown plan – approval | Tariq Esposito | 2026-09-20 | Done
4 | Millbrook planning conditions – check | Jamie Kennedy | 2026-10-04 | Done
5 | Port of Eastholm laydown plan – check | Grace Brown | 2026-09-28 | Blocked
6 | Change order CO-007 assessment – check | Craig Brown | 2026-08-19 | Blocked
7 | Change order CO-007 assessment – check | Kate Davies | 2026-10-01 | Done
8 | Export cable 2 recovery plan (HB-RISK-017) – review | Julia Köhler | 2026-09-16 | Blocked
9 | Export cable 2 recovery plan (HB-RISK-017) – input | Lewis Ross | 2026-09-23 | Done