## Actions
# | Item | Owner | Due | Status
1 | Export cable 2 re-manufacture plan – review | Lewis Walker | 2025-12-11 | Open
2 | Export cable 2 re-manufacture plan – input | Paul Graham | 2025-10-19 | Blocked
3 | Factory acceptance test report – check | Lewis Walker | 2025-12-12 | Open
4 | Factory acceptance test report – check | Ravi Haddad | 2025-10-31 | In progress
5 | Export cable 2 re-manufacture plan – input | Rosie Burns | 2025-10-30 | Open
6 | Factory acceptance test report – update | Lewis Wilson | 2025-11-16 | Open
7 | Cable lay sequence – approval | Duncan Duncan | 2025-11-13 | In progress
8 | Factory acceptance test report – input | Joaquín Novak | 2025-12-15 | Open
9 | Factory acceptance test report – review | Robert Hughes | 2025-12-07 | Done