## Actions
# | Item | Owner | Due | Status
1 | Blade inspection campaign – approval | Oliver Hamilton | 2026-09-17 | Done
2 | Kestrel Ridge availability – input | Ella Smith | 2026-09-30 | Done
3 | T-07 gearbox lessons learned – review | Emre Rossi | 2026-10-18 | In progress
4 | Kestrel Ridge availability – check | Leila Rossi | 2026-09-15 | Open
5 | Blade inspection campaign – update | Olga Kowalczyk | 2026-10-05 | In progress
6 | T-07 gearbox lessons learned – input | Joanne Jones | 2026-10-06 | Open
7 | Blade inspection campaign – check | Mark Taylor | 2026-09-18 | Blocked
8 | Kestrel Ridge availability – review | Stuart Kerr | 2026-09-04 | Open