## Actions
# | Item | Owner | Due | Status
1 | Lender meeting agenda – review | Matthias Vogel | 2026-10-12 | Done
2 | Covenant monitoring – update | Katharina Hansen | 2026-10-24 | Done
3 | Drawdown checklist – update | Hannah Brockmann | 2026-10-27 | Blocked
4 | Lender meeting agenda – approval | Hannah Krause | 2026-10-18 | In progress
5 | Drawdown checklist – input | Omar Popescu | 2026-09-02 | Blocked
6 | Lender meeting agenda – approval | Omar Popescu | 2026-08-29 | In progress
7 | Lender meeting agenda – update | Katharina Hansen | 2026-10-21 | In progress
8 | Drawdown checklist – approval | Hannah Krause | 2026-09-05 | Open
9 | Lender meeting agenda – input | Lisa Zimmermann | 2026-09-11 | Blocked
10 | Lender meeting agenda – review | Marie Braun | 2026-10-04 | Open
11 | Drawdown checklist – update | Matthias Vogel | 2026-10-06 | Open
12 | Covenant monitoring – review | Christian Becker | 2026-10-25 | In progress