## Actions
# | Item | Owner | Due | Status
1 | Weather downtime log – check | Leila Singh | 2026-09-11 | Done
2 | Weather downtime log – approval | Pieter Bakker | 2026-09-01 | Done
3 | MV Sea Atlas daily progress – check | Daan Jansen | 2026-08-23 | Done
4 | MV Sea Atlas daily progress – update | Daan de Vries | 2026-08-18 | Done
5 | Weather downtime log – check | Pieter van den Berg | 2026-08-11 | Done
6 | Weather downtime log – approval | Amelia Johnston | 2026-08-22 | Done
7 | Lift plan – check | Pieter van den Berg | 2026-09-26 | In progress
8 | MV Sea Atlas daily progress – check | Thijs van den Berg | 2026-09-30 | Done
9 | Lift plan – update | Amelia Johnston | 2026-09-19 | In progress
10 | Lift plan – check | Oliver Mackenzie | 2026-08-09 | Blocked
11 | MV Sea Atlas daily progress – review | Sander Smit | 2026-09-19 | In progress
12 | MV Sea Atlas daily progress – check | Ruben de Vries | 2026-08-12 | Done
13 | Weather downtime log – update | Ryan Jones | 2026-08-11 | Blocked