## Actions
# | Item | Owner | Due | Status
1 | Commissioning plan – input | Line Holm | 2026-07-05 | Open
2 | HTS-12 delivery schedule – approval | Laura Schulz | 2026-08-07 | Blocked
3 | Installation manual comments – check | Kasper Holm | 2026-08-05 | Blocked
4 | Commissioning plan – approval | Kasper Dahl | 2026-07-11 | Open
5 | Installation manual comments – approval | Mikkel Dahl | 2026-07-08 | Open
6 | HTS-12 delivery schedule – approval | Vikram Haddad | 2026-06-16 | Open
7 | Installation manual comments – review | Nanna Holm | 2026-07-10 | Done
8 | Commissioning plan – check | Maja Jensen | 2026-07-01 | Open
9 | HTS-12 delivery schedule – approval | Vikram Haddad | 2026-07-03 | Done
10 | HTS-12 delivery schedule – approval | Freja Lund | 2026-07-18 | Done
11 | Commissioning plan – update | Greta Becker | 2026-07-23 | Done