## Actions
# | Item | Owner | Due | Status
1 | ISO 27001 control evidence – check | Christian Hansen | 2026-10-26 | Blocked
2 | ISO 27001 control evidence – update | Liam Clark | 2026-09-14 | Done
3 | Backup restore test – review | Jonas Schröder | 2026-11-09 | Open
4 | Phishing simulation results – input | Katarzyna Nowak | 2026-09-13 | Blocked
5 | Laptop rollout plan – check | Liam Clark | 2026-10-08 | In progress
6 | Backup restore test – approval | Euan Johnston | 2026-09-23 | Done
7 | OpenCloud migration tasks – approval | Tariq Dubois | 2026-11-06 | Open
8 | ISO 27001 control evidence – check | Tariq Dubois | 2026-10-24 | In progress
9 | ISO 27001 control evidence – update | Sindre Haugen | 2026-11-04 | In progress
10 | Phishing simulation results – input | Katarzyna Nowak | 2026-10-09 | Open
11 | Phishing simulation results – approval | Euan Johnston | 2026-09-19 | Blocked
12 | OpenCloud migration tasks – input | Jan Kowalski | 2026-09-28 | Done
13 | Phishing simulation results – review | Hiroshi Novak | 2026-10-27 | Blocked