## Actions
# | Item | Owner | Due | Status
1 | Technician rota – update | Iain Thomson | 2026-09-30 | In progress
2 | Technician rota – update | Lucy Young | 2026-09-10 | Open
3 | Service report summary – check | Morag Paterson | 2026-09-04 | Open
4 | Service report summary – input | Iain Thomson | 2026-09-06 | Open
5 | Technician rota – review | Euan Fraser | 2026-10-07 | Done
6 | Service report summary – review | Oliver Turner | 2026-10-17 | Blocked
7 | Technician rota – approval | Agnieszka Nowak | 2026-09-12 | Open
8 | Blade inspection findings – check | Katarzyna Wiśniewski | 2026-09-21 | In progress
9 | Technician rota – approval | Iain Thomson | 2026-09-23 | Done
10 | Technician rota – update | Euan Fraser | 2026-09-21 | Done
11 | Technician rota – update | Alasdair Turner | 2026-09-09 | In progress
12 | Technician rota – check | Rosie Gray | 2026-10-20 | Open
13 | Blade inspection findings – check | Katarzyna Wiśniewski | 2026-09-06 | Open