## Actions
# | Item | Owner | Due | Status
1 | Logistics plan Port of Eastholm – update | Kenji Nguyen | 2026-08-28 | Blocked
2 | Supplier ESG questionnaire – check | Johan Nilsson | 2026-09-20 | In progress
3 | Blade inspection framework – check | Henning Werner | 2026-10-13 | Open
4 | CTV services tender – input | Lucía Novak | 2026-09-02 | Done
5 | Supplier audit Rhenus – input | Henning Werner | 2026-09-13 | Blocked
6 | CTV services tender – approval | Henning Werner | 2026-10-17 | Open
7 | Supplier audit Rhenus – review | Gordon Ferguson | 2026-08-31 | In progress
8 | Supplier audit Rhenus – update | Lena Müller | 2026-09-24 | In progress
9 | Blade inspection framework – update | Lena Müller | 2026-08-29 | Open
10 | Supplier audit Rhenus – input | Henning Werner | 2026-10-06 | Done
11 | Supplier ESG questionnaire – approval | Frank Koch | 2026-09-13 | Open